Greenwich Association, Inc.

1470 NE 123rd Street, Office #110 • North Miami, FL 33161

GreenwichManager@outlook.com • Tel. 1 (305) 895-0191

Expected Special Assessment for the 40-year structural integrity recertification

Update of November 1, 2024

The Greenwich condominium is undergoing extensive concrete restoration work to obtain a required a 40-year structural integrity recertification for the building from Miami Dade County. In 2023 Restore Construction Company started repairs on the façade and balconies in a project in which Greenwich Association is represented by O&S Engineering. The costs have been successively adjusted as the surface work progresses, uncovering structural deficiencies; it is currently projected to be completed in April 2025 at a total estimated cost of $2,629,321.

Over 50% of the expected work had been completed at a cost of $1,865,165.80. The remaining work is underway mostly on the western façade of the building, where less structural affection is expected. Additional payments to the engineering firm managing the project are around $108,000 to date.

Required electrical upgrades are currently under review and will lead to work at additional cost to the Association as well as to individual unit owners for amounts that cannot yet be established. Upgrades required from the owners include installing, where needed, GFI outlets and smoke detectors. Whether individual units’ electrical panels must be upgraded is to be determined.

On October 1, 2024, the Association hired an engineer as an independent consultant to provide advice in the best interest of owners for the recertification project.

In order to meet the increasing funding requirements of the recertification, in May 2024 the Association obtained a non-revolving interest-only line of credit from Banco Popular of up to $3,350,000 at an interest rate of 6.75% and a maximum 24-month term. The Association is paying the interest on the line of credit drawdowns from the operating budget, which is funded with the monthly maintenance fees.

Once the project is completed, and the final disbursed amount known, there will be a Special Assessment proportionate to the respective ownership share of each unit. If the maximum amount of the line of credit were disbursed, the proportionate share will be as follows and could be paid in full or financed: 2/2 corner units: $20,109; 2/2 interior units: $18,864; and 1/1 units: $12,480. Owners who request the financing will be able to pay their share of the line of credit as a regular term loan of 5, 7, or 10 years at interest rates of 6.75%, 6.80% or 6.85% respectively.

Remediating structural deficits in the parking lot causing severe flooding, also subject to government regulations, is also being quoted and evaluated. These could be included in a Special Assessment but might not be eligible for the Miami-Dade assistance program.

Owners who reside in their units and meet certain requirements may apply for assistance from the Miami-Dade Condominium Special Assessment Program in the form of an interest-free 40-year loan of up to $50,000. Earnings may not exceed $95,620 for individuals, $109,200 for couples, $122,920 for 3-person households, and $136,500 for 4-person households.